## Tasks
Task | Workstream | Owner | Due Date | Status | % Complete
Finalize requirements doc | Planning | Alice Tan | 2026-09-05 | Done | 100%
Stakeholder kickoff meeting | Planning | Alice Tan | 2026-08-31 | Done | 100%
Draft risk register | Planning | Ben Lo | 2026-09-08 | In Progress | 60%
Vendor contract review | Procurement | Chen Wei | 2026-09-07 | Overdue | 30%
Budget approval | Procurement | Chen Wei | 2026-09-14 | In Progress | 50%
Set up dev environment | Development | Divya Rao | 2026-09-09 | Done | 100%
Build authentication module | Development | Divya Rao | 2026-09-16 | In Progress | 40%
API integration testing | Development | Erik Sund | 2026-09-06 | Overdue | 20%
UI design mockups | Design | Farah Idris | 2026-09-12 | In Progress | 70%
Usability testing round 1 | Design | Farah Idris | 2026-09-20 | Not Started | 0%
Prepare training materials | Training | George Kim | 2026-09-25 | Not Started | 0%
Deliver end-user training | Training | George Kim | 2026-10-05 | Not Started | 0%
QA regression testing | Development | Erik Sund | 2026-09-18 | Not Started | 0%
Security review | Development | Divya Rao | 2026-09-04 | Overdue | 10%
Go-live checklist | Deployment | Alice Tan | 2026-09-30 | Not Started | 0%